## Plan 15 Aug 16
Category | Subcategory | Capability | Interface defined | Documentation | Implementation | Tests | Days work remaining | Comments
Simulation |  | Station/Antenna locations | Yes | Partial | Partial | No | 2 | Antenna/station persistence missing
|  | Illumination/Primary beam models | Yes | Partial | No | No | 5 | DISH-SDP ICDs?
|  | Station beam models | Yes | Partial | No | No | 5 | LFAA-SDP ICDs?
|  | Import/export visibilities | Yes | Partial | No | No | 3
|  | Generation of visibility data | Yes | Partial | Yes | Partial | 3
|  | Generation of gain tables with errors | Yes | No | No | No | 5
Calibration | Calibration solvers | Gain solvers | Yes | Partial | Partial | No | 3 | Use Ludwig's implementation of Stefcal?
| Calibration application | Gain application | Yes | No | No | No | 3
|  | Gain interpolation | Yes | No | No | No | 3
| Self-calibration |  | Yes | No | No | No | 3
Visibility plane |  | Phase rotation | Yes | Yes | Partial | Partial | 1 | UVW rotation still needed
| Resampling | Averaging/deaveraging | Yes | No | No | No | 9
Visibility to/from Image | Transforms | Two dimensional | Yes | No | Partial | No | 3 | Crocodile single frequency only
|  | W Projection | Yes | No | Partial | No | 3 | Crocodile single frequency only
|  | AW Projection | Yes | No | Partial | No | 3 | Crocodile single frequency only
|  | AWI Projection | Yes | No | No | No | 9 | Crocodile single frequency only
|  | W snapshots | Yes | No | No | No | 6 | Not present in crocodile
|  | DFT | Yes | Yes | Yes | Partial | 1
|  | FFT | Yes | Yes | Yes | Partial | 1
|  | Faceted transforms | No | No | No | No | 6
| Weighting | Uniform | Yes | No | Partial | No | 3 | Crocodile single frequency only
|  | Briggs | Yes | No | No | No | 1 | Not present in crocodile
|  | Major cycles | Yes | Yes | Yes | Partial | 3
Image plane |  | Source finding | Yes | Yes | Partial | Yes | 3 | Point source only so far
|  | Source fitting | Yes | Partial | Partial | Partial | 6 | Use third party initially
|  | Reprojection | Yes | Yes | No | No | 6 | Use third party initially: reproject.py
|  | Input/output via FITS | Yes | Yes | Yes | Yes | 0
| Deconvolution | MSClean minor cycle (for spectral line) | Yes | Yes | yes | No | 3
|  | MSMFS minor cycle (for continuum) | No | No | No | No | 12
Packaging | DATA-163 support |  | No | No | No | No | 10
| Clean release on Github |  | Yes | Partial | Partial | No | 3
| Reference documentation |  | Yes | Partial | Partial | No | 3
[7 empty] | 130 | Days
[7 empty] | 26 | Weeks